## Worksheet
Topic | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18
Finish by Date | 2023-07-17 | 2023-07-24 | 2023-07-31 | 2023-08-07 | 2023-08-14 | 2023-08-21 | 2023-08-28 | 2023-09-04
Hardware Develelopement | 2023-07-17: Test sensors; 2023-07-24: Order PCB
| Pick final parts | Make CAD | 3d print CAD | DFX
| Develop Firmware |  |  | Contact CM?
App Development | 2023-07-24: Finish MVP; 2023-07-31: find developers
| Create wireframes | Test MVP with users
| create homepage | Get Feedback
Website | 2023-07-17: Create wireframes; 2023-07-24: Test value props
Business Develelopement | 2023-07-17: Grant/ accelerator push; 2023-07-31: Make Deck
| make connections |  | Make Pitch
customer discovery
Figure out software vs hardware dilemma
Notes
website's purpose Is to test product market fit, test what features are wanted by customers and what order, to create a email list, to discover product pricing

## Sample
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Week 14 | Week 15 | Week 16 | Week 17 | Week 18
Date | 30th May | 5th June | 12th June | 19th June | 26th June | 3rd July | 10th July | 17th July | 24th July | 31st July | 7th August | 14th August | 21st August | 28th August | 4th September | 11th September | 18th September | 25th September
Customer Discovery Interviews | Week 1: 4; Week 2: 4; Week 3: 4; Week 4: 4; Week 5: 4; Week 6: 4; Week 7: 4; Week 8: 4; Week 9: 4
Hardware Prototyping | Week 1: identifying product features, hardware requirements and materiality; Week 11: make changes to the prototype
prototyping electrical and hardware parts.
combining all parts and usability testing
Final prototype for demo day
Web Site/App Mock Up | Week 1: Create information architecture; Week 11: adding additional features to the website
Create paper prototypes
Develop core pages for final website
core functionality for the website complete
Business development | Week 1: target customer, value propositions
|  |  | BMC - draft 1 |  |  |  | BMC - draft 2
|  |  |  | feasability and financial plan |  | pricing, conjoint analysis
Investor Meetings
[8 empty] | pitch deck |  |  | pitch deck v2
Marketing | Week 1: work on elevator pitch; Week 10: developing product renders
|  | get feasbility and BMC in place | [9 empty] | set-up kickstarter page and content
Create final pitch deck for presentation
Notes | Week 2: Order sensors and prototyping material; Week 5: Check budget left for prototyping